## Schedule
Order | TASK | AREA | SUMMER GOAL DATE | (S) ACTUAL DATE DONE | WINTER GOAL DATE | (W) ACTUAL DATE DONE | Documentation | Column1
1 | Pay prepaid postage invoice | PRE-COMMITMENT |  |  |  |  | Prepay Postage (Web view) | Crystal needs to update
2 | Update and approve tax back of notices. | PRE-COMMITMENT |  |  |  |  | Back of Notices (Web view) | Crystal needs to update
3 | Request Logos GL Code for new tax year | PRE-COMMITMENT | 2024-06-03 |  |  |  | Change all Logos payment codes to new GL (Web view)
4 | Setup new tax year on Autoagent | PRE-COMMITMENT | 2024-05-01 | 2024-03-25 |  |  | Setup a new tax year in Autoagent (Web view) | Summer 5/27 - 6/11 Winter 10/28 - 11/13
5 | BSA Software update to latest version. | PRE-COMMITMENT |  |  |  |  | Updating BSA Software (Web view) | Crystal will do w/Kyle
6 | Send messages via Autoagent to mortgage companies that have not uploaded a pre-commitment file. | PRE-COMMITMENT | 2024-06-03 |  |  |  | Send messages via Autoagent to mortgage companies that have not uploaded a pre-commitment file. (Web view)
7 | Change all Logos payment codes to new GL | PRE-COMMITMENT | 2024-06-04 |  |  |  | Change all Logos payment codes to new GL (Web view)
8 | Get BIZ import file | PRE-COMMITMENT |  |  |  |  | Business Improvement Zone (Web view)
9 | Get L-4029s from taxing units | PRE-COMMITMENT |  |  |  |  | Get L-4029s from taxing units (Web view)
10 | Attach new DB to shared DB Group. Program setup->4. Administration->:Shared DB Settings | PRE-COMMITMENT |  |  |  |  | New DB Setup (Web view)
11 | Confirm Address information under Taxes Setup | PRE-COMMITMENT |  |  |  |  | New DB Setup (Web view)
12 | Create Summer Annual Installments for Specials Assessments | PRE-COMMITMENT |  |  |  |  | Create Summer Annual Installments for Specials Assessments (Web view)
13 | Use 'New Tax Year Database Wizard' to create new DB. | PRE-COMMITMENT |  |  |  |  | New DB Setup (Web view)
14 | Import values, names and addresses from Assessing using direct import feature. Do not import mortgage codes from previous year. | PRE-COMMITMENT |  |  |  |  | Assessing Options
15 | Review Calculation Options under Taxes Setup | PRE-COMMITMENT |  |  |  |  | Calculation Options
16 | Review Fiscal Year Setup | PRE-COMMITMENT |  |  |  |  | Fiscal Year Setup
17 | Review Interest and Penalty Setup | PRE-COMMITMENT |  |  |  |  | Interest and Penalty Setup
18 | Review Receipt Options under Taxes Setup | PRE-COMMITMENT |  |  |  |  | Receipt Options
19 | Enter into Millage Rate Spreadsheet in master spreadsheet. | PRE-COMMITMENT |  |  |  |  | Enter into Millage Rate Spreadsheet in master spreadsheet. (Web view)
20 | Use millage rate spreadsheet to enter millages into BSA | PRE-COMMITMENT |  |  |  |  | Millage Billing Options | MIKE TO FINISH INSTRUCTIONS
21 | Verify millage tables with County Equalization. | PRE-COMMITMENT |  |  |  |  | Verify millage tables with County Equalization. (Web view)
22 | Get assessing mill levied sheet from assessing. | PRE-COMMITMENT |  |  |  |  | Assessing Millage Sheet (Web view)
23 | Import/Remove delinquent message utility import form County Treasurer | PRE-COMMITMENT |  |  |  |  | Instructions for Local unit Prior Year Delinquent Message (Web view)
24 | Import invoices to taxroll. | PRE-COMMITMENT |  |  |  |  | Invoice, Utilities, Solid Waste to Tax roll (Web view)
25 | Import Solid Waste | PRE-COMMITMENT |  |  |  |  | Invoice, Utilities, Solid Waste to Tax roll (Web view)
26 | Import special assessment EXCEPT PACE to Summer Taxroll | PRE-COMMITMENT
27 | Import BIZ | PRE-COMMITMENT |  |  |  |  | Importing BIZ Assessments (Web view)
28 | Import Utilities | PRE-COMMITMENT |  |  |  |  | RECORD 11/6 AND 11/7 MEETING TO DOCUMENT
29 | Mark installments paid in specials DB using 7/1 posting date. | PRE-COMMITMENT |  |  |  |  | Mark installments paid in specials DB using 7/1 posting date. (Web view)
30 | Review Special Assessment names for accuracy. | PRE-COMMITMENT |  |  |  |  | Special Assessment Options
31 | Tax Bill Review | PRE-COMMITMENT |  |  |  |  | Tax Bill Review (Web view)
32 | Freeze Changes in Assessing. | PRE-COMMITMENT |  |  |  |  | Freeze changes in Assessing (Web view)
33 | RE-RUN DIRECT IMPORT FROM ASSESSING | PRE-COMMITMENT |  |  |  |  | Direct Import from Assessing (Web view)
34 | Adjust sequoia Place after committing | PRE-COMMITMENT |  |  |  |  | Sequoia Place TV (Web view)
34.4 | Import Winter Only PREs from Assessing | PRE-COMMITMENT
34.5 | Check PREA denial parcels | PRE-COMMITMENT |  |  |  |  | Confirm PREA Denials will have 0 PRE for the winter.
35 | Backup Database prior to committing. | PRE-COMMITMENT |  |  |  |  | Backup and Restore Database Instructions (Web view)
36 | Balance PRE/NON-PRE with assessing. | PRE-COMMITMENT |  |  |  |  | Taxes 2023 Master Spreadsheet.xlsx
37 | Balance TV totals with assessing | PRE-COMMITMENT |  |  |  |  | Use balancing tab of master spreadsheet. totals as of 8am on 6/14. when assessing stopped making changes.
38 | Write Floating Values | PRE-COMMITMENT |  |  |  |  | Write Floating Values (Web view)
39 | Commit taxes | COMMITMENT | 2024-06-12 |  |  |  | Commit Taxes (Web view)
40 | Inform Chase to open lockbox | BANKING | 2024-06-24 |  |  |  | Request Lockbox to open 7/2/2024. Chase ELB has been permanently closed.
41 | Download pre commitment files from Autoagent. | PRINTING |  |  |  |  | Download pre commitment files from Autoagent. (Web view)
42 | Import pre-commitment files into BSA. | PRINTING |  |  |  |  | Importing Pre-Commitment Files from Autoagent (Web view)
43 | Insert BOR mortgage codes to prevent bills from going out | PRINTING |  |  |  |  | Insert BOR mortgage codes to prevent bills from going out (Web view)
44 | Assign bill numbers by first sorting by mortgage code. | PRINTING |  |  |  |  | Balancing Tab in master tax spreadsheet.
45 | Update History Files | PRINTING |  |  |  |  | Updating History Files (Web view)
46 | Write floating values. | PRINTING |  |  |  |  | Write Floating Values (Web view)
47 | Create bill printing files and Reconcile number of bills exported. | PRINTING |  |  |  |  | Balancing Tab in master tax spreadsheet. THERE IS A DIFFERENT TEMP-LATE FOR INFO ONLY!
48 | upload bill printing files | PRINTING | 2024-06-14
49 | Point Autoagent Export to new DB | POST-COMMITMENT |  |  |  |  | Kyle.
50 | Email printer about postmark date of tax bills. | POST-COMMITMENT |  |  |  |  | Give printer date bills should be mailed.
51 | Distribute millage sheets with customer service. | POST-COMMITMENT
52 | Export balances to logos and verify logos tax payments are working for each season. | POST-COMMITMENT
53 | Get Up to date Assessing Totals spreadsheet from Assessing | POST-COMMITMENT |  |  |  |  | Assessing Totals Spreadsheets
54 | Invoice Cloud Upload | POST-COMMITMENT |  |  |  |  | When do we really want to do this?
55 | Logos Import File to mark invoices paid | POST-COMMITMENT |  |  |  |  | Revenue Collection Batch 2023-5433, Journal Batch 2023-9527
56 | Receive and review tax bill samples | POST-COMMITMENT
57 | Journal Entry to offset Logos receipt for invoices, utilities, and solid waste. | POST-COMMITMENT |  |  |  |  | Taxes 2023 Master Spreadsheet.xlsx
58 | Summer Taxes Article | POST-COMMITMENT |  |  |  |  | Property Tax July Community Newsletter Article (Web view)
59 | Update installment year in specials so correct year is visible online. | POST-COMMITMENT |  |  |  |  | In Special Assessments Program>Program Setup > Program Settings tab > Cash Receipting Options button. In the window that appears, change the 'Installment Year to use for Interface' to your current installment year.
60 | Calculate Brownfield capture. | POST-COMMITMENT |  |  |  |  | Master spreadsheet
61 | Calculate DDA capture and factor. | POST-COMMITMENT |  |  |  |  | Master spreadsheet
62 | Calculate Smartzone capture. | POST-COMMITMENT |  |  |  |  | Master spreadsheet
63 | Enter deferments. | POST-COMMITMENT
64 | Get list of Brownfield parcels from Assessing. | POST-COMMITMENT |  |  |  |  | This list has partial TVs for parcels also in the DDA. Use for TVs in master spreadsheet.
65 | Send DDA capture report to DDA. | POST-COMMITMENT |  |  |  |  | Master spreadsheet
66 | Bill DDA for Sidewalks and Insurance | POST-COMMITMENT |  |  |  |  | • Sidewalks ○ This is done as part of the DDA Capture. ○ It is calculated as the sidewalk portion of the street millage that applies to the DDA. ○ Invoiced by Tonya with the DDA capture sheet as backup. • Insurance ○ Should come from the premium allocation sheet that Kim helps with. ○ What is last year's invoice number? Need to match against backup.
67 | pay tax billing invoice in correct FY. | POST-COMMITMENT |  |  |  |  | either needs to be processed prior to final prev FY ap run, or PO must be carried forward.
68 | Send brownfield capture to Nathan for review. | POST-COMMITMENT
69 | Journal Entry to record installments transferred to taxroll | POST-COMMITMENT

## Interest and Penalty Setup
Nothing needs to be changed in the interest/penalty calculation options button on summer or winter tabs.
It is also extremely important that the 'Override Interest Calculation Method' field is set to 'Ann Arbor, City' so that our interest and penalty calculations work properly
• Nothing checked under 'Interest/Penalty Charges for Parcels Marked as Deferred…'

## Millage Billing Options
AAPS OPERATING
AAPS SUPP
ALL OTHER MILLAGES
SCHOOL OP FC

## Upload to Bill Printer
need to update with KCI information.

## Seqouia and Lurie Terrace
Parcel | Facility Name | Orig TV
09-29-215-060 | Lurie Terrace | 2579238
90-00-039-015 | Lurie Terrace | 44400
08-24-103-006 | Sequoia Place | 1961259